## 八月份
2013-08
|  |  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
人海8月份工作列表 - App端
App端原型 | 2 | 2013-08-08 | 2013-08-09 12:00
App端需求 - 初稿 | 3 | 2013-08-10 | 2013-08-12 12:00
需求评审 | 1.1 | 2013-08-11 | 2013-08-11 12:00
App端需求 - 修订稿1 | 1 | 2013-08-13 | 2013-08-13 12:00
需求评审 | 1.1 | 2013-08-14 | 2013-08-14 12:00
App端需求 - 终稿 | 1 | 2013-08-15 | 2013-08-15 12:00
需求评审 | 1.1 | 2013-08-16 12:00 | 2013-08-17
App端设计 - 初稿 | 3 | 2013-08-17 12:00 | 2013-08-20
设计评审 | 1.1 | 2013-08-21 | 2013-08-21 12:00
App端设计 - 修订稿1 | 1 | 2013-08-22 | 2013-08-22 12:00
设计评审 | 1.1 | 2013-08-24 | 2013-08-24 12:00
App端设计 - 修订稿2 | 1 | 2013-08-25 | 2013-08-25 12:00
设计评审 | 1.1 | 2013-08-26 12:00 | 2013-08-27
App端设计 - 终稿 | 1 | 2013-08-27 12:00 | 2013-08-28
设计评审 | 1.1 | 2013-08-29 | 2013-08-29 12:00
人海8月份工作列表 - Server端
Server端需求 - 初稿 | 2 | 2013-08-08 | 2013-08-09 12:00
需求评审 | 1.1 | 2013-08-10 | 2013-08-10 12:00
Server端需求 - 修订稿1 | 1 | 2013-08-12 | 2013-08-12 12:00
需求评审 | 1.1 | 2013-08-12 | 2013-08-13 12:00
Server端需求 - 终稿 | 1 | 2013-08-15 | 2013-08-15 12:00
需求评审 | 1.1 | 2013-08-15 | 2013-08-16
Server端设计 - 初稿 | 3 | 2013-08-17 12:00 | 2013-08-20
设计评审 | 1.1 | 2013-08-17 12:00 | 2013-08-20 12:00
Server端设计 - 修订稿1 | 2 | 2013-08-22 | 2013-08-23 12:00
设计评审 | 1.1 | 2013-08-22 | 2013-08-23 12:00
Server端设计 - 修订稿2 | 1 | 2013-08-25 | 2013-08-25 12:00
设计评审 | 1.1 | 2013-08-25 | 2013-08-26
Server端设计 - 终稿 | 1 | 2013-08-27 12:00 | 2013-08-28
设计评审 | 1.1 | 2013-08-27 12:00 | 2013-08-28 12:00
人海8月份工作列表 - 共同
WebSocket demo | 4 | 2013-08-06 | 2013-08-07 12:00
Chris上班 | 4 | 2013-08-06 | 2013-08-09 12:00
Chris上班 | 15 | 2013-08-10 | 2013-08-28 12:00
Patrick 100 %
Patrick 100 %
Patrick 100 %, Tomas 100 %, Chris 20 %
Patrick 100 %
Patrick 100 %, Tomas 100 %, Chris 20 %
Patrick 100 %
Patrick 100 %, Tomas 100 %, Chris 20 %
Patrick 100 %
Patrick 100 %, Tomas 100 %, Chris 20 %
Patrick 100 %
Patrick 100 %, Tomas 100 %, Chris 20 %
Patrick 100 %
Patrick 100 %, Tomas 100 %, Chris 20 %
Patrick 100 %
Patrick 100 %, Tomas 100 %, Chris 20 %
Tomas 100 %
Patrick 100 %, Tomas 100 %, Chris 20 %
Tomas 100 %
Patrick 100 %, Tomas 100 %, Chris 20 %
Tomas 100 %
Patrick 100 %, Tomas 100 %, Chris 20 %
Tomas 100 %
Patrick 100 %, Tomas 100 %, Chris 20 %
Tomas 100 %
Patrick 100 %, Tomas 100 %, Chris 20 %
Tomas 100 %
Patrick 100 %, Tomas 100 %, Chris 20 %
Tomas 100 %
Patrick 100 %, Tomas 100 %, Chris 20 %
Patrick 100 %, Tomas 100 %
Chris 100 %
Chris 79 %
Note on I4: Patrick 100%
Note on M5: Patrick 100%
Note on O6: Tomas 100% Chris 20%
Note on S7: Patrick 100%
Note on U8: Patrick 100% Tomas 100% Chris 20%
Note on W9: Patrick 100%
Note on Z10: Patrick 100% Tomas 100% Chris 20%
Note on AB11: Patrick 100%
Note on AI12: Patrick 100% Tomas 100% Chris 20%
Note on AK13: Patrick 100%
Note on AO14: Patrick 100% Tomas 100% Chris 20%
Note on AQ15: Patrick 100%
Note on AT16: Patrick 100% Tomas 100% Chris 20%
Note on AV17: Patrick 100%
Note on AY18: Patrick 100% Tomas 100% Chris 20%
Note on I21: Tomas 100%
Note on M22: Tomas 100% Chris 20%
Note on Q23: Tomas 100%
Note on Q24: Chris 20%
Note on S24: Tomas 100% Chris 20%
Note on W25: Tomas 100%
Note on W26: Chris 20%
Note on Y26: Patrick 100% Tomas 100% Chris 20%
Note on AB27: Tomas 100%
Note on AB28: Chris 20%
Note on AH28: Patrick 100% Tomas 100% Chris 20%
Note on AK29: Tomas 100%
Note on AK30: Chris 20%
Note on AM30: Patrick 100% Chris 20%
Note on AQ31: Tomas 100%
Note on AQ32: Chris 20%
Note on AS32: Patrick 100% Tomas 100% Chris 20%
Note on AV33: Tomas 100%
Note on AV34: Chris 20%
Note on AX34: Patrick 100% Tomas 100% Chris 20%
Note on E37: Patrick 100% Tomas 100%
Note on E38: Chris 100%
Note on M39: Chris 79%

## MileStone
Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb
2013-08-01 | 2013-08-08 | 2013-08-15 | 2013-08-22 | 2013-08-29 | 2013-09-05 | 2013-09-12 | 2013-09-19 | 2013-09-26 | 2013-10-03 | 2013-10-10 | 2013-10-17 | 2013-10-24 | 2013-10-31 | 2013-11-07 | 2013-11-14 | 2013-11-21 | 2013-11-28 | 2013-12-05 | 2013-12-12 | 2013-12-19 | 2013-12-26 | 2014-01-02 | 2014-01-09 | 2014-01-16 | 2014-01-23 | 2014-01-30 | 2014-02-06 | 2014-02-13 | 2014-02-20 | 2014-02-27
需求
设计
功能编码测试
App上架
性能测试
2013-11-01
Mid-review

## 风险管理
项目风险管理表
基本信息
项目名称 | 人海
启动时间 | 2013-08-01
项目成员 | 邓柯、陈崇磐、李诚
风险管理
序号 | 风险描述 | 发生概率 | 影响程度 | 应对计划 | 责任人 | 风险状态
1899-12-31 | Java技能不足，尤其是多线程部分掌握不够，导致Server不能达到设计的性能容量 | 高 | 大 | 加强设计的评审，不冒然开始编码 | 陈崇磐 | 未发生
1900-01-01 | VPS带宽不能满足要求 | 高 | 大 | 选择VPS之前，慎重考虑，多家比较 | 邓柯 | 未发生
1900-01-02 | 由于不可抗力因素，团队完整性受到破坏 | 低 | 极大 | 尽力确保6个月的稳定期 | 陈崇磐 | 未发生
1900-01-03 | 李诚下半年的时间投入不可控 | 高 | 中 | 尽量让李诚负责零散的任务 | 陈崇磐 | 未发生
1900-01-04 | AppStore不允许随机视频聊天的App | 低 | 极大 | 尝试使用开发者账号上载一个App | 邓柯 | 未发生
1900-01-05 | 多线程测试或者性能测试的技术方案还不清楚 | 高 | 大 | 技术储备 | 陈崇磐 | 未发生

## TDD
- | 由需求来决定测试集
- | 由测试来决定代码
需求
设计/建模
单元测试
编码
系统测试
代码框架
性能测试
Jenkins每天利用单元测试用例检验目前的编写的代码是否正确，不断迭代，直至实现所有功能
以设计生成的代码框架为基础编写的用例，保证覆盖所有需求
如果利用生成的代码框架不能覆盖所有的需求，说明设计不够详细，需要继续细化设计