## 九月份
|  |  |  | 2013-08 |  | 2013-09
|  |  |  | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
人海9月份工作列表 - App端
通信模块 | 2 | 2013-09-03 12:00 | 2013-09-05
用户数据模块 | 1 | 2013-09-01 12:00 | 2013-09-02
WebRTC模块 | 1 | 2013-09-02 12:00 | 2013-09-03
公共模块 | 1 | 2013-08-31 12:00 | 2013-09-01
App数据模块 | 1 | 2013-08-30 12:00 | 2013-08-31
日志模块 | 0.5 | 2013-08-30 | 2013-08-30
功能模块测试 | 3 | 2013-09-05 12:00 | 2013-09-08
界面 - 启动页 | 0.5 | 2013-09-08 12:00 | 2013-09-08 12:00
界面 - 主界面 | 1 | 2013-09-09 | 2013-09-09 12:00
界面 - 设备卡片 | 1 | 2013-09-12 | 2013-09-12 12:00
界面 - 印象卡片 | 1 | 2013-09-13 | 2013-09-13 12:00
界面 - 兴趣卡片 | 2 | 2013-09-14 | 2013-09-15 12:00
界面 - 等待匹配 | 0.5 | 2013-09-10 12:00 | 2013-09-10 12:00
界面 - 确认匹配 | 1 | 2013-09-16 | 2013-09-16 12:00
界面 - 视频聊天 | 2 | 2013-09-17 | 2013-09-18 12:00
界面 - 双方评价 | 2 | 2013-09-19 | 2013-09-20 12:00
界面 - 配置 | 1 | 2013-09-11 | 2013-09-11 12:00
界面 - 提示 | 0.5 | 2013-09-10 | 2013-09-10
界面 - 帮助 | 3 | 2013-09-21 | 2013-09-23 12:00
业务功能测试 | 3 | 2013-09-24 | 2013-09-26 12:00
人海9月份工作列表 - Server端
db
数据库操作基础类 | 1.5 | 2013-09-03 | 2013-09-04
JSON
JSON功能模块 | 3 | 2013-09-04 12:00 | 2013-09-07
log
日志管理类 | 1 | 2013-09-07 12:00 | 2013-09-08
test
基础功能测试函数 | 2 | 2013-09-08 12:00 | 2013-09-10
业务测试模块 | 4 | 2013-08-30 | 2013-09-02 12:00
business
设备管理类 | 3 | 2013-09-10 12:00 | 2013-09-13
在线设备池 | 2 | 2013-09-13 12:00 | 2013-09-15
随机业务设备池 | 2 | 2013-09-17 12:00 | 2013-09-19
随机业务调度器 | 1 | 2013-09-19 12:00 | 2013-09-20
业务会话 | 2 | 2013-09-15 12:00 | 2013-09-17
业务会话池 | 2 | 2013-09-20 12:00 | 2013-09-22
WebSocket通信模块 | 1.5 | 2013-09-22 12:00 | 2013-09-23 12:00
兴趣业务设备池 | 1 | 2013-09-24 | 2013-09-24 12:00
兴趣业务调度器 | 2 | 2013-09-25 | 2013-09-26 12:00
全局配置管理 | 1 | 2013-09-27 | 2013-09-27 12:00
统计信息显示 | 0.5 | 2013-09-28 | 2013-09-28
人海9月份工作列表 - 性能测试
性能测试设计 | 2 | 2013-09-27 | 2013-09-28 12:00
性能测试编码 | 4 | 2013-09-29 | 2013-09-30 12:00
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Patrick 100 %, Tomas 100 %
Patrick 100 %, Tomas 100 %
Note on N4: Patrick 100%
Note on J5: Patrick 100%
Note on L6: Patrick 100%
Note on H7: Patrick 100%
Note on F8: Patrick 100%
Note on E9: Patrick 100%
Note on R10: Patrick 100%
Note on X11: Patrick 100%
Note on Y12: Patrick 100%
Note on AE13: Patrick 100%
Note on AG14: Patrick 100%
Note on AI15: Patrick 100%
Note on AB16: Patrick 100%
Note on AM17: Patrick 100%
Note on AO18: Patrick 100%
Note on AS19: Patrick 100%
Note on AC20: Patrick 100%
Note on AA21: Patrick 100%
Note on AW22: Patrick 100%
Note on BC23: Patrick 100%
Note on M27: Tomas 100%
Note on P29: Tomas 100%
Note on V31: Tomas 100%
Note on X33: Tomas 100%
Note on E34: Tomas 100%
Note on AB36: Tomas 100%
Note on AH37: Tomas 100%
Note on AP38: Tomas 100%
Note on AT39: Tomas 100%
Note on AL40: Tomas 100%
Note on AV41: Tomas 100%
Note on AZ42: Tomas 100%
Note on BC43: Tomas 100%
Note on BE44: Tomas 100%
Note on BI45: Tomas 100%
Note on BK46: Tomas 100%
Note on BI49: Patrick 100%
Note on BL49: Patrick 100% Tomas 100%
Note on BM50: Patrick 100% Tomas 100%

## 八月份
2013-08-01
|  |  |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 | 24 | 25 | 26 | 27 | 28 | 29
人海8月份工作列表 - App端
App端原型 | 3 | 2013-08-08 | 2013-08-10 12:00 | [5 empty] | 20 |  | 50 |  | 100
App端需求 - 初稿 / 评审 | 3 | 2013-08-11 | 2013-08-13 12:00 | [11 empty] | 20 |  | 100
App端需求 - 修订稿1 / 评审 | 2.5 | 2013-08-14 | 2013-08-16
App端需求 - 终稿 / 评审 | 1.5 | 2013-08-16 12:00 | 2013-08-17 12:00 | [15 empty] | 100
App端设计 - 初稿 / 评审 | 3 | 2013-08-18 | 2013-08-20 12:00 | [18 empty] | 100
App端设计 - 修订稿1 / 评审 | 2.5 | 2013-08-21 | 2013-08-23
App端设计 - 修订稿2 / 评审 | 1.5 | 2013-08-23 12:00 | 2013-08-24 12:00
App端设计 - 终稿 / 评审 | 1 | 2013-08-25 | 2013-08-25 12:00
App测试Case初稿 / 评审 | 2 | 2013-08-26 | 2013-08-27 12:00 | [20 empty] | 20 |  | 60 |  | 100
App测试Case终稿 / 评审 | 2 | 2013-08-28 | 2013-08-29 12:00
人海8月份工作列表 - Server端
Server端需求 - 初稿 / 评审 | 3 | 2013-08-08 | 2013-08-10 12:00 | [5 empty] | 30 |  | 70 |  | 100
Server端需求 - 修订稿1 / 评审 | 2.5 | 2013-08-11 | 2013-08-13 | [11 empty] | 100
Server端需求 - 终稿 / 评审 | 1.5 | 2013-08-13 12:00 | 2013-08-14 12:00 | [14 empty] | 100
Server端设计 - 初稿 / 评审 | 3 | 2013-08-15 | 2013-08-17 12:00 | [18 empty] | 80 |  | 100 |  |  |  | 100
Server端设计 - 修订稿1 / 评审 | 3 | 2013-08-18 | 2013-08-20 12:00 | [26 empty] | 50 |  | 100
Server端设计 - 修订稿2 / 评审 | 2.5 | 2013-08-21 | 2013-08-23
Server端设计 - 终稿 / 评审 | 1.5 | 2013-08-23 12:00 | 2013-08-24 12:00
Server测试Case - 初稿 / 评审 | 3 | 2013-08-25 | 2013-08-27 12:00 | [20 empty] | 20 |  | 30 |  | 40 |  | 40 |  | 40 |  | 90 |  | 100
Server测试Case - 终稿 / 评审 | 2 | 2013-08-28 | 2013-08-29 12:00
性能测试 / 文档评审 | 4 | 2013-08-10 | 2013-08-29 12:00
人海8月份工作列表 - 共同
WebSocket demo | 4 | 2013-08-06 | 2013-08-07 12:00 |  | 50 |  | 100
Chris上班 | 4 | 2013-08-06 | 2013-08-09 12:00
Chris上班 | 12 | 2013-08-10 | 2013-08-24 12:00
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Patrick 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Tomas 100 %
Patrick 100 %, Tomas 100 %
Chris 100 %
Chris 80 %
Patrick 100 %
Patrick 100 %
Tomas 100 %
Tomas 100 %
Chris 20 %
Note on I4: Patrick 100%
Note on AH4: 界面重新设计 在做图片
Note on O5: Patrick 100%
Note on U6: Patrick 100%
Note on Z7: Patrick 100%
Note on AC8: Patrick 100%
Note on AI9: Patrick 100%
Note on AN10: Patrick 100%
Note on AQ11: Patrick 100%
Note on AS12: Patrick 100%
Note on AW13: Patrick 100%
Note on I16: Tomas 100%
Note on O17: Tomas 100%
Note on T18: Tomas 100%
Note on W19: Tomas 100%
Note on AC20: Tomas 100%
Note on AI21: Tomas 100%
Note on AN22: Tomas 100%
Note on AQ23: Tomas 100%
Note on AW24: Tomas 100%
Note on M25: Chris 20%
Note on E28: Patrick 100% Tomas 100%
Note on E29: Chris 100%
Note on M30: Chris 80%

## MileStone
Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb
2013-08-01 | 2013-08-08 | 2013-08-15 | 2013-08-22 | 2013-08-29 | 2013-09-05 | 2013-09-12 | 2013-09-19 | 2013-09-26 | 2013-10-03 | 2013-10-10 | 2013-10-17 | 2013-10-24 | 2013-10-31 | 2013-11-07 | 2013-11-14 | 2013-11-21 | 2013-11-28 | 2013-12-05 | 2013-12-12 | 2013-12-19 | 2013-12-26 | 2014-01-02 | 2014-01-09 | 2014-01-16 | 2014-01-23 | 2014-01-30 | 2014-02-06 | 2014-02-13 | 2014-02-20 | 2014-02-27
需求
设计
功能编码测试
App上架
性能测试
2013-11-01
Mid-review

## 风险管理
项目风险管理表
基本信息
项目名称 | 人海
启动时间 | 2013-08-01
项目成员 | 邓柯、陈崇磐、李诚
风险管理
序号 | 风险描述 | 发生概率 | 影响程度 | 应对计划 | 责任人 | 风险状态
1 | Java技能不足，尤其是多线程部分掌握不够，导致Server不能达到设计的性能容量 | 高 | 大 | 加强设计的评审，不冒然开始编码 | 陈崇磐 | 未发生
2 | VPS带宽不能满足要求 | 高 | 大 | 选择VPS之前，慎重考虑，多家比较 | 邓柯 | 关闭
3 | 由于不可抗力因素，团队完整性受到破坏 | 低 | 极大 | 尽力确保6个月的稳定期 | 陈崇磐 | 已发生
4 | 李诚下半年的时间投入不可控 | 高 | 中 | 尽量让李诚负责零散的任务 | 陈崇磐 | 关闭
5 | AppStore不允许随机视频聊天的App | 低 | 极大 | 尝试使用开发者账号上载一个App | 邓柯 | 未发生
6 | 多线程测试或者性能测试的技术难度 | 高 | 大 | 技术储备 | 陈崇磐 | 未发生

## TDD
- | 由需求来决定测试集
- | 由测试来决定代码
需求
设计/建模
单元测试
编码
系统测试
代码框架
性能测试
Jenkins每天利用单元测试用例检验目前的编写的代码是否正确，不断迭代，直至实现所有功能
以设计生成的代码框架为基础编写的用例，保证覆盖所有需求
如果利用生成的代码框架不能覆盖所有的需求，说明设计不够详细，需要继续细化设计